## Recurrent Expenditure
Annual Schedule of Planned Procurement Activities 2023/2024
RECURRENT EXPENDITURE
No. | Project Number | Brief Description | UNSPSC Code | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Standstill period (if applicable) – No. of days | Contract Type
General Administration
1 | 02/004/10 | Office Stationery and Supplier: Paper, paper clips, file jackets, temporary file jackets, manilla folders, steno pads, post its, glue sticks, liquid glue, 3-tiered trays, dips, pens, ink cartridges, rulers, erasers, treasury tags, stamp pad, envelopes, notebooks, ixl apex binder, binder combs, mountain tape, masking tape, scotch tape, duct tape, binder clips, bristol board, transparency film, highlighters, whiteboard markers, permanent markers, scissors, Milo, Teas, Water, Milk, Sugar/Condensed Milk, Sanitary Coffee Cups, Dishwashing liquid, Lysol Spray, Hand Sanitizers, Napkins, Telephone Cleaner | 44120000 | October, 2023 | December, 2024 | Quarterly | Request for Quotation | Not Applicable | Invoice/ Quotation
2 | 02/004/10 | Office Stationery and Supplier: Paper, paper clips, file jackets, temporary file jackets, manilla folders, steno pads, post its, glue sticks, liquid glue, 3-tiered trays, dips, pens, ink cartridges, rulers, erasers, treasury tags, stamp pad, envelopes, notebooks, ixl apex binder, binder combs, mountain tape, masking tape, scotch tape, duct tape, binder clips, bristol board, transparency film, highlighters, whiteboard markers, permanent markers, scissors, Milo, Teas, Water, Milk, Sugar/Condensed Milk, Sanitary Coffee Cups, Dishwashing liquid, Lysol Spray, Hand Sanitizers, Napkins, Telephone Cleaner | 44120000 | January, 2024 | March, 2024 | Quarterly | Request for Quotation | Not Applicable | Invoice/ Quotation
3 | 02/004/10 | Office Stationery and Supplier: Paper, paper clips, file jackets, temporary file jackets, manilla folders, steno pads, post its, glue sticks, liquid glue, 3-tiered trays, dips, pens, ink cartridges, rulers, erasers, treasury tags, stamp pad, envelopes, notebooks, ixl apex binder, binder combs, mountain tape, masking tape, scotch tape, duct tape, binder clips, bristol board, transparency film, highlighters, whiteboard markers, permanent markers, scissors, Milo, Teas, Water, Milk, Sugar/Condensed Milk, Sanitary Coffee Cups, Dishwashing liquid, Lysol Spray, Hand Sanitizers, Napkins, Telephone Cleaner | 44120000 | April, 2024 | June, 2024 | Quarterly | Request for Quotation | Not Applicable | Invoice/ Quotation
4 | 02/004/10 | Office Stationery and Supplier: Paper, paper clips, file jackets, temporary file jackets, manilla folders, steno pads, post its, glue sticks, liquid glue, 3-tiered trays, dips, pens, ink cartridges, rulers, erasers, treasury tags, stamp pad, envelopes, notebooks, ixl apex binder, binder combs, mountain tape, masking tape, scotch tape, duct tape, binder clips, bristol board, transparency film, highlighters, whiteboard markers, permanent markers, scissors, Milo, Teas, Water, Milk, Sugar/Condensed Milk, Sanitary Coffee Cups, Dishwashing liquid, Lysol Spray, Hand Sanitizers, Napkins, Telephone Cleaner | 44120000 | July, 2024 | September, 2024 | Quarterly | Request for Quotation | Not Applicable | Invoice/ Quotation
5 |  | Security Services: To pay charges associated with all contracted security services. | 92120000 |  |  | Monthly | Open Bidding | Not Applicable | Fixed Term Contract
6 |  | Training (Sensitization of Procurement Processes) | 86100000 | July, 2024 | July, 2024 | 3 Days | Request for Quotation | Not Applicable | Invoice/ Quotation
7 |  | Printing of manuals, forms, brochures, flyers | 82121500 | July, 2024 | July, 2024 | 5 days | Request for Quotation | Not Applicable | Invoice/ Quotation
8 |  | Office Stamps for Various Departments | 44121500 | January, 2024 | January, 2024 | 7 days | Request for Quotation | Not Applicable | Invoice/ Quotation
9 |  | Hosting of Monthly Meetings where there's catering of meals and drinks | 80141902 | October, 2023 | October, 2023 | Monthly | Request for Quotation | Not Applicable | Invoice/ Quotation
10 |  | Payment of Electricity | 83101800 | October, 2023 | October, 2023 | 2 months | Sole Source Selection | Not Applicable
11 |  | Payment of Water Rates | 83101500 | October, 2023 | October, 2023 | 2 months | Sole Source Selection | Not Applicable
12 |  | Payment of Telephone Services | 83111501 | October, 2023 | October, 2023 | Monthly (Payments) | Single Source | Not Applicable
13 |  | Rent/Lease Office Accomodation | 80131500 | October, 2023 | October, 2023 | Monthly (payment) | Single Source | Not Applicable | Fixed Term Contract
14 |  | Supply and Delivery of Ink/Toners: For all Departments | 44120000 | October, 2023 | October, 2023 | 5 days | Request for Quotation | Not Applicable | Invoice/ Quotation
15 |  | Supply and Delivery of Ink/Toners: For all Departments | 44120000 | January, 2024 | January, 2024 | 5 days | Request for Quotation | Not Applicable | Invoice/ Quotation
16 |  | Supply and Delivery of Ink/Toners: For all Departments | 44120000 | April, 2024 | April, 2024 | 5 days | Request for Quotation | Not Applicable
17 |  | Insurance coverage for General Administration Building | 84131505 | October, 2023 | October, 2023 | 12 months | Limited Bidding | Not Applicable | Fixed Term Contract
18 |  | Office Equipment: To purchase office equipment, such as photocopiers, printers, computers, router,Laptop,Printer/scanner/copier, Tablet with internet access,Mobile telephone with internet access, Digital camera and case, Projector | 43212100 | January, 2024 | March, 2024 | 3 months | Request for Quotations | Not applicable | Invoice/Quotations
19 |  | Other Minor Equipment: To purchase minor equipment eg Refridgerator, Microwave Oven, Electric Kettle, Laminating Machine | 44100000 | January, 2024 | March, 2024 | 3 months | Request for Quotations | Not applicable | Invoice/Quotations
20 |  | Purchase of Chemical Free Archival Boxes for storage of Tender Documents. | 44120000 | April, 2024 | April, 2024 | 14 Days | Request for Quotation | Not applicable | Invoice/Quotations
21 |  | Hosting of Conferences, Seminars and Other Functions (Emancipation King and Queen, Graduation for Entrepreneurial Training) | 80141902 | August, 2024 | September, 2024 | 2 months | Request for Quotation | Not Applicable | Invoice/ Quotation
22 |  | 1st Borough Month Celebration: Rental Vehicle, Rental of Tents, Chairs, Tables, Photograher, Caterer, Purchase of Banners, Water, Umbrella, Trophy, plaques, |  | June, 2024 | July, 2024 | 1 month | Request for Quotation | Not Applicable | Invoice/Quotations
23 |  | Purchase one customized podium |  | June, 2024 | June, 2024 | 2 weeks | Request for Quotation | Not Applicable | Invoice/Quotations
Facilities Department
1 |  | Maintenance Services for Elevator | 72101500 | July, 2024 | July, 2024 | 12 months | Limited Bidding | Not Applicable | Fixed Term Contract
2 |  | Mainteance Services of Generator | 72101500 | April, 2024 | April, 2024 | 3 Days | Request for Quotation | Not Applicable | Invoice/ Quotation
3 |  | Grounds Maintenance | 72101500 | July, 2024 | July, 2024 | 12 months | Limited Bidding | Not Applicable | Fixed Term Contract
4 |  | Purchase of three flag poles | 72101500 | April, 2024 | April, 2024 | 7 days | Request for Quotation | Not Applicable | Invoice/ Quotation
5 |  | Technical Services - Plumbing | 72101500 | July, 2024 | July, 2024 | 2 weeks | Request for Quotation | Not Applicable | Invoice/ Quotation
6 |  | Maintenance Service for Aircondition Units | 72101500/72151200 | January, 2024 | January, 2024 | 12 months | Limited Bidding | Not Applicable | Fixed Term Contract
7 |  | Maintenance Services of FireAlarm System | 7210500 | April, 2024 | April, 2024 | 3 days | Request for Quotation | Not Applicable | Fixed Term Contract
8 |  | Building Exterior Cleaning Service - WASH AND CLEAN GLASS | 7210500 | June, 2024 | June, 2024 | 1 day | Request for Quotation | Not Applicable | Invoice/ Quotation
9 |  | Reprairs to leak: DISCHARGE OF POTABLE WATER PUMP PACKAGE AND SKIMMIN OF LIFTSTATION | 7210500 | June, 2024 | June, 2024 | 1 week | Request for Quotation | Not Applicable | Invoice/ Quotation
10 |  | Repairs: (2) 90 DEGREE ELBOW IN UNDERGROUND MAIN LINE | 7210500 | June, 2024 | June, 2024 | 1 week | Request for Quotation | Not Applicable | Invoice/ Quotation
Technical Department
1 |  | Maintenace of Vehicles: To purchase all parts and consumables for vehicles (Light Trucks, SUVs, Trucks, Trailers and other Heavy Equipment) to conduct preventive maintenance, such as oil, filters and tyres. To pay charges associated with additional service cost to vehicles. | 78181500 | October, 2023 | September, 2024 | 2 months | Request for Quotation | Not applicable | Invoice/Quotation
2 |  | Maintenance of Backhoes: To purchase all parts for Backhoes to conduct preventive maintenance, such as oil, filters and tyres. To purchase parts for Backhoes for major repairs such as, alternators, engine, transmissions etc. To pay charges associated with additional service cost to vehicles. | 78181500 | Apr. - Jun. 2024 | Apr. - Jun. 2024 | 6-8 weeks | Request for Quotations | Not applicable | Invoice/ Quotation
3 |  | Minor Equipment purchases: Chop saw, Bushcutters, wacker head etc | 56000000 | July, 2024 | August, 2024 | 1 month | Request for Quotation | Not applicable | Invoice/Quotation
4 |  | Fuel and Lubricants: To purchase diesel, gasoline, renew fleet cards etc. | 15000000 | October, 2023 | September, 2024 | Weekly | Sole Selective Tendering | Not applicable | Fixed Term Contract
5 |  | Vehicles: To purchase 2 Vehicle | 25100000 | Otober, 2023 | April, 2024 | 6 months | Limited Bidding | 10 days | Fixed Term Contract
6 |  | Materials and Supplies: To purchase machine shop consumables, welding tools and plate sections, tyre tools and repair material, carpentry tools and materials, equipment bay tools and materials. | 27000000 | Jan. - Mar. 2024 | Jan. - Mar. 2024 | 4-6 weeks | Request for Quotations | Not applicable | Invoice/ Quotation
7 |  | Materials and Supplies: Purchase of road marking paint, (white and yellow), thermoplastic materials (blocks and beads), sign making material (aluminum sheets, shapes, pipes, tape), gravel, cement, controllers, mast arms | 39121700 | June, 2024 | June, 2024 | 3 weeks | Request for Quotation | Not applicable | Invoice/Quotation
8 |  | Purchase of Electrical Supplies | 39121700 | April, 2024 | June, 2024 | 3 weeks | Request for Quotation | Not applicable | Invoice/Quotation
9 |  | Purchase of Plumbling Supplies | 72151100 | June, 2024 | June, 2024 | 2 weeks | Request for Quotation | Not applicable | Invoice/Quotation
10 |  | Purchase of Aggregates | 30111800 | June, 2024 | June, 2024 | 2 weeks | Request for Quotation | Not applicable | Invoice/Quotation
11 |  | Purchase of Safety Vest | 46181500 | July, 2024 | July, 2024 | 2 weeks | Request for Quotation | Not applicable | Invoice/Quotation
12 |  | Payment of Electricity | 83101800 | October, 2023 | October, 2023 | 2 months | Sole Source Selection | Not Applicable | Fixed Term Contract
13 |  | Payment of Water Rates | 83101500 | October, 2023 | October, 2023 | 2 months | Sole Source Selection | Not Applicable | Fixed Term Contract
14 |  | Payment of Telephone Services | 83111501 | October, 2023 | October, 2023 | Monthly (Payments) | Single Source | Not Applicable | Fixed Term Contract
Information Technology
1 |  | Network Equipment and Software Purchases (Server) | 81111500 | May, 2024 | May, 2024 | 1-3 months | Request for Quotation | Not applicable | Invoice/Quotation
2 |  | Upgrade of IP TELEPHONE SYSTEM | 81111500 | October, 2023 | March, 2024 | 6 months | Request for Proposal | Not applicable | Invoice/ Quotation
3 |  | Purchase of 16 Laptop | 43211508 | June, 2024 | July, 2024 | 3-5 weeks | Request for Quotation | Not applicable | Invoice/Quotation
Public Health
1 |  | Pest Control | 10191700 | October, 2023 | September, 2024 | 12 months | Request for Quotation | Not Applicable | Invoice/Quotation
2 |  | Purchase of Brown Paper Pags | 24111500 | April, 2024 | April, 2024 | 1 week | Request for Quotation | Not Applicable | Invoice/Quotation
3 |  | Purchase of Paint Supplies | 31211900 | July, 2024 | July, 2024 | 2 weeks | Request for Quotation | Not Applicable | Invoice/Quotation
4 |  | Removal of Garbage | 76121600 | October, 2023 | September, 2024 | Daily | Open Bidding | Not Applicable | Fixed Term Contract
5 |  | Supply of Powerwasher for PH | 47121800 | January, 2024 | February, 2024 | 1 month | Request for Proposal | Not applicable | Invoice/ Quotation
6 |  | Payment of Electricity | 83101800 | October, 2023 | September, 2024 | 2 months | Sole Source Selection | Not Applicable | Fixed Term Contract
7 |  | Payment of Water Rates | 83101500 | October, 2023 | September, 2024 | 2 months | Sole Source Selection | Not Applicable | Fixed Term Contract
8 |  | Payment of Telephone Services | 83111501 | October, 2023 | September, 2024 | Monthly (Payments) | Single Source | Not Applicable | Fixed Term Contract
9 |  | Rent/Lease Office Accomodation | 80131500 | October, 2023 | September, 2024 | Monthly (payment) | Single Source | Not Applicable | Fixed Term Contract
Disaster Management Unit
1 |  | Purchase of Safety Vest | 46181500 | June 10, 2024 | June 12, 2024 | 3 days | Request for Quotation | Not applicable | Invoice/Quotation
2 |  | Payment of Electricity | 83101800 | October, 2023 | September, 2024 | 2 months | Sole Source Selection | Not Applicable | Fixed Term Contract
3 |  | Payment of Water Rates | 83101500 | October, 2023 | September, 2024 | 2 months | Sole Source Selection | Not Applicable | Fixed Term Contract
4 |  | Payment of Telephone Services | 83111501 | October, 2023 | September, 2024 | Monthly (Payments) | Single Source | Not Applicable | Fixed Term Contract
5 |  | Purchase of Tarpaulin | 31162800 | May, 2024 | May, 2024 | 3 days | Request for Quotation | Not applicable | Invoice/Quotation
6 |  | Purchase of Filling Sand | 30111800 | June, 2024 | June, 2024 | 2 days | Request for Quotation | Not applicable | Invoice/Quotation
7 |  | Purchase New Air Condition Units | 72151200 | June, 2024 | June, 2024 | 6 weeks | Request for Quotation | Not applicable | Invoice/Quotation
Municipal Police Department
1 |  | Purchase New Air Condition Units | 72151200 | June, 2024 | June, 2024 | 6 weeks | Request for Quotation | Not applicable | Invoice/Quotation
E
-
mail: dmrc.tenders@gmail.com
Diego Martin Borough Corporation
# 1
-
2
Ken Valley Circular, West Vale Park, Diego Martin
(
:
(868) 633
-
4461
Fax
: 633
-
4461
Hot Line
: 633
-
1533

## DP_162
Annual Schedule of Planned Procurement Activities 2023/2024
#162 IMPROVEMENTS TO MARKETS AND ABATTOIRS
No. | Project Number | Brief Description | UNSPSC Code | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Standstill period (if applicable) – No. of days | Contract Type
1 | 162 | Turnstile Compound: Construction of Store room: 3.6m x 3m x 2.4m; Construction of Box Drain: 63m x 0.9m x 0.6m inclusive of Steel Grill. Construction of Fence Wall: 30m x 2.4m x 0.2m; Renovation of Washroom Facilities. Supply and installation of Wire Fence: 50m x 2.4m inclusive of installation of Gate | 72120000 | 2nd Quarter | 4th Quarter | 6 months | Open Bidding | Not applicable | Fixed Term Contract
E
-
mail: dmrc.tenders@gmail.com
Diego Martin Borough Corporation
# 1
-
2
Ken Valley Circular, West Vale Park, Diego Martin
(
:
(868) 633
-
4461
Fax
: 633
-
4461
Hot Line
: 633
-
1533

## DP_371
Annual Schedule of Planned Procurement Activities 2023/2024
#371 DISASTER PREPARDNESS
No. | Project Number | Brief Description | UNSPSC Code | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Standstill period (if applicable) – No. of days | Contract Type
1 | 371 | One (1) only Vantage Pro2+ Wireless Station | 72153300 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 6 weeks | Request for Quotation | Not applicable | Invoice/ Quotation
2 | 371 | One (1) only DJI Mavic 3 Enterprise | 25132103 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 6 weeks | Request for Quotation | Not applicable | Invoice/ Quotation
E
-
mail: dmrc.tenders@gmail.com
Diego Martin Borough Corporation
# 1
-
2
Ken Valley Circular, West Vale Park, Diego Martin
(
:
(868) 633
-
4461
Fax
: 633
-
4461
Hot Line
: 633
-
1533

## DP_166
Annual Schedule of Planned Procurement Activities 2023/2024
PROCUREMENT OF MAJOR VEHICLES & EQUIPMENT
No. | Project Number | Brief Description | UNSPSC Code | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Standstill period (if applicable) – No. of days | Contract Type
1 | 166 | One (1)TDX -650 Roller | 24101723 | 2nd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 | 1 - 3 months | Request for Quotation | Not applicable | Invoice/ Quotation
2 | 166 | One (1) 4 Post Lift- Rolling Jack | 25174810 | 2nd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 | 6 months | Request for Quotation | Not applicable | Invoice/ Quotation
3 | 166 | One (1) 80 Gallon Vertical Air Compressor | 40151600 | 2nd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 | 3 months | Request for Quotation | Not applicable | Invoice/ Quotation
4 | 166 | One (1) 25 Tyre Changer 24" diameter, Bead Seater in Jaws | 25191755 | 2nd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 | 3 months | Request for Quotation | Not applicable | Invoice/ Quotation
5 | 166 | One (1) MH320 Helper Arm |  | 2nd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 | 3 months | Request for Quotation | Not applicable | Invoice/ Quotation
6 | 166 | One (1) Masport HXL 75V Vacuum Pump | 40151700 | 2nd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 | 1-3 months | Request for Quotation | Not applicable | Invoice/ Quotation
7 | 166 | One (1) only 13 Seater Civillian Bus | 25101500 | 2nd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 | 3-6 months | Open Bidding | Not applicable | Fixed Term Contract
E
-
mail: dmrc.tenders@gmail.com
Diego Martin Borough Corporation
# 1
-
2
Ken Valley Circular, West Vale Park, Diego Martin
(
:
(868) 633
-
4461
Fax
: 633
-
4461
Hot Line
: 633
-
1533

## DP_375
Annual Schedule of Planned Procurement Activities 2023/2024
#375 MUNICIPAL POLICE EQUIPMENT
No. | Project Number | Brief Description | UNSPSC Code | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Standstill period (if applicable) – No. of days | Contract Type
1 | 375 | Twenty (20) Pepper Spray and Holsters | 92101500 | 3rd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 | 1 month | Single Source | Not Applicable | Invoice/ Quotation
2 | 375 | Ten (10) Tazer Gun Kits | 46111600 | 3rd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 | 1 month | Single Source | Not Applicable | Invoice/ Quotation
3 | 375 | Ten (10) Additional Cartridges | 46111600 | 3rd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 | 1 month | Single Source | Not Applicable | Invoice/ Quotation
4 | 375 | Three (3) Plate Carriers | 46111600 | 3rd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 | 1 month | Single Source | Not Applicable | Invoice/ Quotation
5 | 375 | Six (6) Additional Cartridge | 46111600 | 3rd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 | 1 month | Single Source | Not Applicable | Invoice/ Quotation
6 | 375 | Six (6) Body Cam | 46171610 | 3rd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 | 2 months | Single Source | Not Applicable | Invoice/ Quotation
7 | 375 | One (1) Docking Station | 43211602 | 3rd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 | 1 month | Single Source | Not Applicable | Invoice/ Quotation
8 | 375 | One (1) Dock License (Per Yr) | 43211602 | 3rd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 | 1 month | Single Source | Not Applicable | Invoice/ Quotation
9 | 375 | Five (5) Holsters | 46101801 | 3rd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 | 14 days | Single Source | Not Applicable | Invoice/ Quotation
10 | 375 | Four (4) Ligh Safety Kit | 46182407 | 3rd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 | 1 month | Single Source | Not Applicable | Invoice/ Quotation
11 | 375 | Three (3) Batons | 49161707 | 3rd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 | 1 month | Single Source | Not Applicable | Invoice/ Quotation
12 | 375 | Three (3) Baton Holster | 49161707 | 3rd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 | 1 month | Single Source | Not Applicable | Invoice/ Quotation
13 | 375 | Four (4) Handcuffs | 46151601 | 3rd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 | 1 month | Single Source | Not Applicable | Invoice/ Quotation
14 | 375 | Four (4) Handcuff Case | 46151601 | 3rd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 | 1 month | Single Source | Not Applicable | Invoice/ Quotation
15 | 375 | Five (5) Radio Base Units | 43191518 | 3rd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 | 1 month | Single Source | Not Applicable | Invoice/ Quotation
16 | 375 | Two (2) APX Mobile Radio | 43191518 | 3rd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 | 3 months | Single Source | Not Applicable | Invoice/ Quotation
17 | 375 | Two (2) Mobile Installation | 43191518 | 3rd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 | 5 days | Single Source | Not Applicable | Invoice/ Quotation
18 | 375 | Two (2) Shredders |  | 3rd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 | 14 days | Request for Quotation | Not Applicable | Invoice/ Quotation
19 | 375 | Two (2) Law Volumes and Updates | 60103502 | 3rd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 | 5 days | Single Source | Not Applicable | Invoice/ Quotation
20 | 375 | One (1) Manual Projector Screen (Wall Mounted) | 45111607 | 3rd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 | 1 month | Request for Quotation | Not Applicable | Invoice/ Quotation
21 | 375 | One (1) Tripod Projector Screen | 45111609 | 3rd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 | 1 month | Request for Quotation | Not Applicable | Invoice/ Quotation
22 | 375 | Two (2) Lazer Pointers | 43211600 | 3rd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 | 5 days | Request for Quotation | Not Applicable | Invoice/ Quotation
23 | 375 | Two (2) Wifi Extenders | 43211600 | 3rd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 | 5 days | Request for Quotation | Not Applicable | Invoice/ Quotation
24 | 375 | One (1) Acer Laptop | 43211508 | 3rd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 | 1 month | Request for Quotation | Not Applicable | Invoice/ Quotation
25 | 375 | One (1) Projector | 45111609 | 3rd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 | 1 month | Request for Quotation | Not Applicable | Invoice/ Quotation
26 | 375 | Four Webcams | 43211600 | 3rd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 | 5 days | Request for Quotation | Not Applicable | Invoice/ Quotation
27 | 375 | Two (2) External Hard Drive 2TB | 43211600 | 3rd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 | 5 days | Request for Quotation | Not Applicable | Invoice/ Quotation
E
-
mail: dmrc.tenders@gmail.com
Diego Martin Borough Corporation
# 1
-
2
Ken Valley Circular, West Vale Park, Diego Martin
(
:
(868) 633
-
4461
Fax
: 633
-
4461
Hot Line
: 633
-
1533

## DP_379
Annual Schedule of Planned Procurement Activities 2023/2024
#379 MUNICIPAL POLICE VEHICLES
No. | Project Number | Brief Description | UNSPSC Code | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Standstill period (if applicable) – No. of days | Contract Type
1 | 379 | One (1) only Toyota Hilux | 25101507/25101702 | 2nd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 | 3 months | Open Bidding | Not applicable | Fixed term contract
2 | 379 | One (1) only Toyota Rav 4 | 25101507/25101702 | 2nd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 | 3 months | Open Bidding | Not applicable | Fixed term contract
E
-
mail: dmrc.tenders@gmail.com
Diego Martin Borough Corporation
# 1
-
2
Ken Valley Circular, West Vale Park, Diego Martin
(
:
(868) 633
-
4461
Fax
: 633
-
4461
Hot Line
: 633
-
1533

## DP_159
Annual Schedule of Planned Procurement Activities 2023/2024
#159 DRAINAGE AND IRRIGATION PROGRAMME
No. | Project Number | Brief Description | UNSPSC Code | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Standstill period (if applicable) – No. of days | Contract Type
1 | 159 | HILLSIDE DRIVE: Construction of Box Drain: 65m x 0.6m x 0.6m. To scarify and pave roadway with hot asphalt mix: 103m x 3.6m x 0.076m | 72141205 | 2nd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 |  | Limited Bidding | Not applicable | Fixed term contract
2 | 159 | NEIGHBOUR’S AVENUE: Construction of box drains: 55m x 0.5m x 0.6m & 7m x 0.6m x 0.6m; Kerbwall: 102m x 0.2m x 0.15m; Slipper drain: 12m x 0.3m x 0.15m; Driveway: 4m x 2.5m x 0.15m. To reform and pave roadway with hot asphalt mix: 55m x 4m x 0.051m | 72141205 | 2nd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 |  | Limited Bidding | Not applicable | Fixed term contract
3 | 159 | VERIEL DRIVE: Construction of Box Drain: 100m x 0.6m x 0.6m inclusive of two (2) Driveways: 5m x 2m x 0.2m & 4m x 2m x 0.2m | 70171800 | 2nd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 |  | Limited Bidding | Not applicable | Fixed term contract
4 | 159 | LP #89 UPPER DUNDONAL HILL: Construction of Box Drain: 30m x 0.9m x 0.9m | 70171800 | 2nd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 |  | Limited Bidding | Not applicable | Fixed term contract
5 | 159 | LP #66 SPRING ROAD: Construction of Box Drain: 35m x 0.9m x 0.9m | 70171800 | 2nd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 |  | Limited Bidding | Not applicable | Fixed term contract
6 | 159 | BIG YARD: Construction of Box Drain: 54m x 0.6m x 0.6m; 250 Steps; (1m x 0.3m x 0.2m); Fabrication & Installation of Railing | 72141205 | 2nd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 |  | Limited Bidding | Not applicable | Fixed term contract
7 | 159 | UPPER HAIG STREET: Construction of Box Drain: 70m x 0.6m x 0.6m | 70171800 | 2nd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 |  | Limited Bidding | Not applicable | Fixed term contract
8 | 159 | SEAVIEW HILL (ON THE RIGHT): Construction of Box Drain: 100m x 0.6m x 0.6m; Steps: 100m 250 (1m x 0.3m x 0.2m); Fabrication & installation of 135m of Railing | 72141205 | 2nd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 |  | Limited Bidding | Not applicable | Fixed term contract
9 | 159 | UPPER FACTORY ROAD. UPPER HILLVIEW DR. EXT: Construction of Box Drain: 100m x 0.6m x 0.6m; Steps: 250m (1.2m x 0.2m x 0.3m); Fabrication & installation of 135m of Railing | 72141205 | 2nd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 |  | Limited Bidding | Not applicable | Fixed term contract
10 | 159 | QUARRY STREET: Construction of Box Drain: 68m x 0.6m x 0.6m | 70171800 | 2nd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 |  | Limited Bidding | Not applicable | Fixed term contract
11 | 159 | RANCH TERRACE: Construction of Box Drain: 65m x 1.2m x 1.2m inclusive of incisions: 4m x 1m | 70171800 | 2nd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 |  | Limited Bidding | Not applicable | Fixed term contract
12 | 159 | UPPER MERCER EXTENSION: Construction of Box Drain: 70m x 0.6m x 0.6m | 70171800 | 2nd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 |  | Limited Bidding | Not applicable | Fixed term contract
13 | 159 | UPPER SAGANGAR: Construction of Box Drain: 65m x 1.2m x 1.2m | 70171800 | 2nd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 |  | Limited Bidding | Not applicable | Fixed term contract
14 | 159 | LP #70 UPPER HILLVIEW DR. CONTINUATION: Construction of Box Drain: 37m x 0.6m x 0.6m | 70171800 | 2nd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 |  | Limited Bidding | Not applicable | Fixed term contract
15 | 159 | LP # 15A/2 UPPER WATERHOLE COCORITE: Construction of Box Drain: 65m x 0.6m x 0.6m; Catchment Pit: 3(0.9m x 0.9m x 0.9m); Footpath: 26m x 1.2m x 0.15m; Sidewall: 16m x 1.2m x 0.15m; Slabs: 2(1.4m x 0.9m x 0.15m) Rehabilitation of Steps: 54m long | 72141205 | 2nd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 |  | Limited Bidding | Not applicable | Fixed term contract
16 | 159 | UPPER HARDING PLACE, COCORITE: Construction of Box Drain: 60m x 0.6m x 0.6m (using a step down method) Construction of three (3) Catchment pits: 3(0.9m x 0.9m x 0.9m) | 72141205 | 2nd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 |  | Limited Bidding | Not applicable | Fixed term contract
17 | 159 | UPPER WATERHOLE, COCORITE: Construction of Box Drain: 60m x 0.6m x 0.6m (using a step down method) Construction of three (3) Catchment pits: 3(0.9m x 0.9m x 0.9m) | 72141205 | 2nd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 |  | Limited Bidding | Not applicable | Fixed term contract
18 | 159 | TONCABEAN TRACE: Construction of Box Drain:32m x 0.5m x 0.3m; Driveway: 4.5m x 0.5m x 0.1m | 70171800 | 2nd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 |  | Limited Bidding | Not applicable | Fixed term contract
19 | 159 | UPPER FAUSTIN TRACE: Construction of Box Drain:60m x 0.3m x 0.3m; Driveway: 6m x 1m x 0.2m | 70171800 | 2nd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 |  | Limited Bidding | Not applicable | Fixed term contract
20 | 159 | LP #9 BACK - A YARD: Construction of Box Drain: 65m x 1.2m x 1.2m inclusive of incisions: 4m x 1m | 70171800 | 2nd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 |  | Limited Bidding | Not applicable | Fixed term contract
21 | 159 | LP #4 COCO JAH: Construction of Box Drain: 45m x 0.6m x 0.6m (using a step down method) Construction of three (3) Catchment pits: 3(0.9m x 0.9m x 0.15m) | 70171800 | 2nd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 |  | Limited Bidding | Not applicable | Fixed term contract
22 | 159 | DOMINGTON GARDENS: Construction of Box Drain: 77m x 1m x 0.6m | 70171800 | 2nd Quarter Fiscal 2023/2024 | 3rd Quarter Fiscal 2023/2024 |  | Limited Bidding | Not applicable | Fixed term contract
E
-
mail: dmrc.tenders@gmail.com
Diego Martin Borough Corporation
# 1
-
2
Ken Valley Circular, West Vale Park, Diego Martin
(
:
(868) 633
-
4461
Fax
: 633
-
4461
Hot Line
: 633
-
1533

## DP_164
Annual Schedule of Planned Procurement Activities 2023/2024
#164 LOCAL ROADS AND BRDIGES PROGRAMME
No. | Project Number | Brief Description | UNSPSC Code | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Standstill period (if applicable) – No. of days | Contract Type
1 | 164 | LP #38 SEA TRACE: To reform and pave roadway with hot asphalt mix:90m x 4m x 0.076m | 72141104 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 1 month | Limited Bidding | Not applicable | Fixed term contract
2 | 164 | LP #35 SEA TRACE: To reform and pave roadway with hot asphalt mix: 68m x 4m x 0.076m | 72141104 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 1 month | Limited Bidding | Not applicable | Fixed term contract
3 | 164 | CUMMINGS LANE: Construction of a Retaining Wall: 39m x 1.8m x0.2m | 72152707 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 1 month | Limited Bidding | Not applicable | Fixed term contract
4 | 164 | DUNDONALD HILL: To reform and pave roadway with hot asphalt mix: 150m x 4.5m x 0.051m | 72141104 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 1 month | Limited Bidding | Not applicable | Fixed term contract
5 | 164 | BELLE VUE ROAD: To resurface and pave roadway with hot asphalt mix: 122m x 4.5m x 0.051m | 72141104 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 1 month | Limited Bidding | Not applicable | Fixed term contract
6 | 164 | ABOUD CIRCULAR: To resurface and pave roadway with hot asphalt mix: 150m x 4.2m x 0.051m | 72141104 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 1 month | Limited Bidding | Not applicable | Fixed term contract
7 | 164 | EBENEZER LINK ROAD: Resurface roadway with hot asphalt mix: 59m x 3.5m x 0.051m; Construction of Kerbwall: 29m x 0.4m x 0.2m; Slipper Drain: 29m x 0.3m x 0.051m | 72141104 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 1 month | Limited Bidding | Not applicable | Fixed term contract
8 | 164 | ABEL STREET: To resurface roadway with hot asphalt mix: 90m x 5m x 0.051m | 72141104 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 1 month | Limited Bidding | Not applicable | Fixed term contract
9 | 164 | TODMAN STREET: To reform and pave roadway with hot asphalt mix: 150m x 5m x 0.076m | 72141104 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 1 month | Limited Bidding | Not applicable | Fixed term contract
10 | 164 | WALKER STREET: To pave roadway with hot asphalt mix: 170m x 5m x 0.076m | 72141104 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 1 month | Limited Bidding | Not applicable | Fixed term contract
11 | 164 | ASH STREET: To resurface roadway with hot asphalt mix: 130m x 5m x 0.051m | 72141104 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 1 month | Limited Bidding | Not applicable | Fixed term contract
12 | 164 | HOLIDAY PARK: Resurface roadway with hot asphalt mix: 180m x 5.1m x 0.051m | 72141104 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 1 month | Limited Bidding | Not applicable | Fixed term contract
13 | 164 | LP #52 SINNANAN: Resurface roadway with hot asphalt mix: 100m x 3.8m x 0.051m | 72141104 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 1 month | Limited Bidding | Not applicable | Fixed term contract
14 | 164 | EVERGREEN WALK EXTENSION: To reform and resurface roadway with hot asphalt mix: 95m x 3.6m x 0.076m; Construction of Kerbwall: 170m x 0.3m x 0.15m; Slipper Drain: 110m x 0.3m x 0.15m & Driveways: 4(4m x 1.2m x 0.15m) | 72141104 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 1 month | Limited Bidding | Not applicable | Fixed term contract
15 | 164 | STUART ROAD: To scarify and pave roadway with hot asphalt mix: 200m x 6m x 0.051m | 72141104 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 1 month | Limited Bidding | Not applicable | Fixed term contract
16 | 164 | RUBY FELIX ROAD: To resurface roadway with hot asphalt mix: 65m x 6m x 0.051m | 72141104 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 1 month | Limited Bidding | Not applicable | Fixed term contract
17 | 164 | LP #84 UPPER LA PUERTA: Construction of a Retaining Wall: 50m x 1.5m x 0.2m | 72152707 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 1 month | Limited Bidding | Not applicable | Fixed term contract
18 | 164 | LP # 23/23 MOKA ROAD: Resurface roadway with hot asphalt mix: 200m x 6m x 0.051m; Construction of Box Drain: 5m x 0.6m x 0.8m | 72141104 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 1 month | Limited Bidding | Not applicable | Fixed term contract
19 | 164 | UPPER FAUSTIN TRACE: To pave roadway with hot asphalt mix: 60m x 4m x 0.076m | 72141104 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 1 month | Limited Bidding | Not applicable | Fixed term contract
20 | 164 | BASCANT STREET: Resurface roadway with hot asphalt mix: 138m x 4.5m x 0.051m | 72141104 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 1 month | Limited Bidding | Not applicable | Fixed term contract
21 | 164 | LP #3 LAZARE STREET: Resurface roadway with hot asphalt mix: 54m x 5.6m x 0.051m | 72141104 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 1 month | Limited Bidding | Not applicable | Fixed term contract
22 | 164 | LP #9 COOPERATIVE DRIVE: Resurface roadway with hot asphalt mix: 300m x 3.4m x 0.051m | 72141104 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 1 month | Limited Bidding | Not applicable | Fixed term contract
23 | 164 | LP #12 ALYCE GLEN GARDENS: Resurface roadway with hot asphalt mix: 75m x 4.8m x 0.051m | 72141104 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 1 month | Limited Bidding | Not applicable | Fixed term contract
24 | 164 | LP#50 BACK A YARD HUMMINGBIRD CIRCULAR: Resurface roadway with hot asphalt mix: 300m x 3.6m x 0.051m; To construct box drain: 22m x 0.45m x 0.45m; Swale Drain: 5m x 0.6m x 0.2m and Driveway: 4m x 1.2m x 0.15m.051m | 72141104 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 1 month | Limited Bidding | Not applicable | Fixed term contract
25 | 164 | PRESIDENT WEISMAN AVENUE: Resurface roadway with hot asphalt mix: 264m x 5.5m x 0.051m | 72141104 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 1 month | Limited Bidding | Not applicable | Fixed term contract
26 | 164 | HARDING PLACE, COCORITE: Construction of Retaining Wall: 12m x 1.2m x 0.2m and capping of existing Wall: 14m x 1.2m x 0.2m. To resurface roadway with hot asphalt mix: 20m x 4.5m x 0.051m & 80m x 5.5m x 0.051m | 72141104 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 1 month | Limited Bidding | Not applicable | Fixed term contract
27 | 164 | LP #15 POWDER MAGAZINE ROAD: To resurface roadway with hot asphalt mix: 160m x 8m x 0.051m; To construct Swale Drain: 4(7m x 0.6m x 0.2m) | 72141104 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 1 month | Limited Bidding | Not applicable | Fixed term contract
28 | 164 | CHOW QUAN AVENUE: Construction of Kerbwall: 78m x 0.2m x 0.15m, Slipper Drain:89m x 0.3m x 0.076m; Driveways: 4m x 1.7m x 0.2m & 5m x 1.7m x 0.2m; Swale Drain: 20m x 0.6m x 0.2m & 4m x 0.6m x 0.2m | 72152707 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 1 month | Limited Bidding | Not applicable | Fixed term contract
29 | 164 | LP #2&3 HERRERA TRACE: Resurface roadway with hot asphalt mix: 71m x 5.6m x 0.051m | 72141104 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 1 month | Limited Bidding | Not applicable | Fixed term contract
30 | 164 | BACK STREET: Resurface roadway with hot asphalt mix: 150m x 5m x 0.051m | 72141104 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 1 month | Limited Bidding | Not applicable | Fixed term contract
31 | 164 | SPRING FLOW ROAD: Resurface roadway with hot asphalt mix: 120m x 5m x 0.051m; Construction of Kerbwall and slipper drain: 91m x 0.2m x 0.15m 91m x 0.3m x 0.076m and 108m x 0.2m x 0.15m & 108m x 0.3m x 0.076m | 72141104 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 1 month | Limited Bidding | Not applicable | Fixed term contract
32 | 164 | CROWN TRACE: To reform and resurface roadway with hot asphalt mix: 80m x 6m x 0.076m | 72141104 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 1 month | Limited Bidding | Not applicable | Fixed term contract
33 | 164 | SMITH HILL VIA W.M.R THOMPSON CIRCULAR: To pave roadway with hot asphalt mix: 200m x 5m x 0.051m | 72141104 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 1 month | Limited Bidding | Not applicable | Fixed term contract
34 | 164 | FRANCOIS STREET EXT.: To resurface roadway with hot asphalt mix: 36m x 6m x 0.076m | 72141104 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 1 month | Limited Bidding | Not applicable | Fixed term contract
35 | 164 | BENEDICTINE STREET: To resurface roadway with hot asphalt mix: 45m x 6m x 0.051m | 72141104 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 1 month | Limited Bidding | Not applicable | Fixed term contract
E
-
mail: dmrc.tenders@gmail.com
Diego Martin Borough Corporation
# 1
-
2
Ken Valley Circular, West Vale Park, Diego Martin
(
:
(868) 633
-
4461
Fax
: 633
-
4461
Hot Line
: 633
-
1533

## DP_160
Annual Schedule of Planned Procurement Activities 2023/2024
#160 DEVELOPMENT OF RECREATIONAL FACILITIES
No. | Project Number | Brief Description | UNSPSC Code | Proposed date for Issue of Bidding Documents | Expected Delivery/ Completion Date | Estimated Project Duration (for works and services) | Procurement Method | Standstill period (if applicable) – No. of days | Contract Type
1 | 160 | Carenage Basketball Court – Supply and Installation of lighting to Basketball Court | 39111612 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 15 days | Limited Bidding | Not Applicable | Fixed term contract
2 | 160 | Point Cumana Basketball Court – Supply and Installation of lighting to Basketball Court | 39111612 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 15 days | Limited Bidding | Not Applicable | Fixed term contract
3 | 160 | La Horquetta Playfield - Supply and installation of lighting to Playfield | 39111612 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 15 days | Limited Bidding | Not Applicable | Fixed term contract
4 | 160 | Point Cumana Park – Supply and Installation of Bench Sets, Wire Fence and lighting of Play Park | 72154013 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 30 days | Limited Bidding | Not Applicable | Fixed term contract
5 | 160 | Surprise Grounds – To construct Bleacher & Public Convenience: 8m x 12m x 3.2m | 95121714 | 3rd Quarter Fiscal 2023/2024 | 4th Quarter Fiscal 2023/2024 | 30 days | Limited Bidding | Not Applicable | Fixed term contract
E
-
mail: dmrc.tenders@gmail.com
Diego Martin Borough Corporation
# 1
-
2
Ken Valley Circular, West Vale Park, Diego Martin
(
:
(868) 633
-
4461
Fax
: 633
-
4461
Hot Line
: 633
-
1533